| Tasks | Components | Steps | Resources | Project Manager | Status/Completion Date |
| --- | --- | --- | --- | --- | --- |
| Establish Goals/Vision for the Chaplaincy | Purpose Background Mission Statement | 1. Define the purpose of the chaplaincy 2. Research the background of chaplaincy programs 3. Develop a mission statement for the program | Sample Chaplain Policies Sample Purpose, Background and Mission Statement |  |  |
| Identify Potential Chaplains | Identify people of faith inside the agency Share vision of chaplaincy with local clergy Find out what clergy of first responders might be a good fit | 1. Compile a list of potential chaplains within the agency 2. Meet with local clergy to share vision and identify potential candidates 3. Discuss the duties and responsibilities of a fire chaplain | Tips on identifying potential Chaplains Sample Chaplain Duties |  |  |
| Secure Training for your Chaplain | Identify the training considered to be best practices that are recommended Identify the training required for chaplaincy deployments. | 1. Identify best practices for chaplaincy training 2. Determine the required training for chaplaincy deployments | Chaplaincy training (Fire) Law Enforcement Chaplaincy Training Clinician Awareness Program FEMA NIMS 100-800 Peer Support (See training section in peer support section of toolkit) |  |  |
|  | Develop and maintain a way to track CEU’s | Establish a system for tracking CEU’s | CEU Guidance |  |  |
| Create Chaplaincy SOG/SOP | Chain of command Activation process Confidentiality components |  | Sample Chaplain Policies |  |  |
| Obtain buy in from the members and perform an informational campaign | Develop a list of talking points to be discussed Conduct routine station visits to meet the members in a comfortable setting |  | Sample Talking Points |  |  |
| Financial considerations | Training costs Travel expenses Uniforms Volunteer/Paid Incidentals Phone Radio Business cards | 1. Determine the costs associated with the program 2. Develop a budget for the program | Sample Costs and Revenue items |  |  |
| Daily Operation of Program | Conduct station visits (the chaplaincy is all about relationships and relationships are all about time) Respond to critical incidents Visit sick/injured members | 1. Schedule routine station visits 2. Respond to critical incidents as needed 3. Visit sick/injured members as needed |  |  |  |
| Maintain your Program | Help your Chaplain stay connected through national, state, and local gatherings | 1. Assist chaplains in attending national, state, and local gatherings to stay connected 2. Review and update program | Federation of Fire Chaplains (firechaplains.org) https://2ndalarmproject.org/ https://ucfrestores.com/training/peer-support/react-training-program/ Clinician Awareness Program Florida Firefighter Safety and Health Collaborative Events Guidance on reviewing your Chaplaincy program |  |  |
| Additional Resources |  |  | ORGANIZATIONS - Federation of Fire Chaplains (firechaplains.org) - Regional training - Annual conference - Sample SOGs - International Critical Incident Stress Foundation (icisf.org) - Crisis intervention training - American Red Cross (redcross.org) - Victim support - FEMA (fema.gov) - Incident command training |  |  |