| Tasks | Components | Steps | Resources | Project Manager | Date Completed |
| --- | --- | --- | --- | --- | --- |
| Identify inpatient programs | List of inpatient programs in the community | 1. Research and compile a comprehensive list of inpatient programs in the community. 2. Identify specialized inpatient treatment providers. | Research tips and questions for facilities, first responder departments in your area |  |  |
| Develop referral network | List of vetted programs and providers for referral | 1. Identify programs and providers with inpatient services that align with your department's needs. 2. Vet these programs and providers. 3. Develop a referral network with contact information. 4. Create a “Backdoor Process” for First Responders in Crisis | Identify, vet and referral process, First Responder Referral Process example |  |  |
| Establish follow-up protocols | Protocols for members who have gone through inpatient stay | 1. Develop a protocol for team members who have gone through an inpatient stay and may have behavioral health concerns upon returning to work. 2. Establish a plan for follow-up care. | Return to work procedure |  |  |
| Develop training program | Training for Peer Team members and Supervisors on inpatient services | 1. Identify topics that team members need to know about inpatient services. 2. Develop training materials. 3. Deliver training to team members. | training materials, Suicide Safety Plan example, Suicidal Member algorithm |  |  |
| Assess effectiveness of program | Evaluation of inpatient program's impact on team members | 1. Identify metrics for evaluating the effectiveness of the inpatient program. 2. Collect data on team members who have utilized inpatient services. 3. Analyze data and assess program impact. | Sample Evaluation Metrics, Data collection tools, mental health professionals, project management software |  |  |
| Monitor and adjust program | Ongoing evaluation and adjustments to inpatient program | 1. Regularly review data and feedback on the inpatient program. 2. Make necessary adjustments to improve the program's effectiveness. | Data collection tools, mental health professionals, project management software |  |  |