| K9 Support Task Book |  |  |  |  |
| --- | --- | --- | --- | --- |
| Tasks | Components | Resources | Project Manager | Status/Completion Date |
| Establish goals/vision for program | Define purpose, background, and mission statement | - Samples from other local departments with programs or from FFSHC K9 mission statement K9 purpose, background and mission statement example | Project Manager | [Completion Date] |
|  | Research and review existing programs and mission statements | - Local fire departments with their own programs - Local therapy dog organization - AAII (Animal Assisted Intervention International) standards for therapy dogs 2019 - National standards for AACR (Animal Assisted Crisis Response) 2010 |  |  |
| Decide on type of K9 program your organization will support | Explore options for K9 programs - External agency coming in for station visits - - Use your own responders with their own dogs internally - Station dog or Peer Support K9 team component | K9 Program examples | Project Manager | [Completion Date] |
|  | 2. Research and review existing K9 programs | - Local pet shelters or rescues - Animal Services – K9s for Warriors - National therapy dog organizations such as Alliance of therapy dogs, Pet Partners, Love on a Leash, Therapy Dogs International and Bright and Beautiful Therapy Dogs - National Crisis Response K9 agencies such as National Crisis Response K9s, Hope Crisis Response K9s |  |  |
|  | 3. Determine the most suitable K9 program for your organization | K9 Program selection guide |  |  |
| Select your handler and source your dog | 1. Determine the requirements for the K9 team | - Peer training model/models accepted by FFSHC such as UCF Reacts, CISM, IAFF model. - K9 training for basic obedience, sociability, professional dog trainers, local K9 therapy dog organizations, - Petco for basic obedience and the Canine Good Citizen (CGC) obedience training, etc. - National therapy dog organizations such as Alliance of therapy dogs, Pet Partners, Love on a Leash, Therapy Dogs International and Bright and Beautiful Therapy Dogs for their requirements and bylaws - National Crisis Response K9 agencies such as National Crisis Response K9s, Hope Crisis Response K9s | Project Manager | [Completion Date] |
|  | 2. Select suitable handlers for the K9 team | - Interested personnel or retirees - Local therapy dog organizations - National therapy dog organizations - National Crisis Response K9 agencies Handler selection for K9 programs |  |  |
|  | 3. Source and select a suitable K9 | Sourcing and selecting a K9 |  |  |
| Create policy or SOG | 1. Determine the policy requirements | - Chain of Command - Peer Response or Station dog rules - Roles and Responsibilities (expectations of K9 behavior) - Training and Certification - Ongoing monthly training requirements - Addressing behavior issues - K9 ownership - Vet care and procedures - Response/Activation of K9 team - K9 Grooming Standards | Project Manager | [Completion Date] |
|  | 2. Develop the policy and SOG | Sample K9 Policy | - Police and Fire and other agencies that have K9 programs |  |
| Create buy-in from staff | -Develop an informational campaign -City/County administration -Senior Staff -Members of the department | Informational Campaign ideas |  |  |