| Outpatient Services Task Book |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Tasks | Steps | Components | Resources | Project Manager | Due Date |
| Identify the services and resources already available at your agency | 1. Gather information on current available services and resources. 2. Document the gathered information. | Behavioral health services, employee assistance programs, peer support programs, chaplain services, etc. | Agency resources and information Guidance on gathering information on services and resources |  | TBD |
| Develop list of outpatient service providers | 1. Research and identify potential providers. 2. Evaluate providers for quality and cultural competence. 3. Compile a list of approved providers. | Outpatient therapy, medication management, substance use treatment | UCF RESTORES, Redline Rescue, Blue Line Rescue, Gold Line Rescue, 2nd Alarm Project & the 10-4 Center for Responder Resiliency outpatient provider guidance |  | TBD |
| Develop list of inpatient treatment providers | 1. Research and identify potential inpatient treatment providers. 2. Evaluate providers for quality and cultural competence. 3. Compile a list of approved inpatient providers. | Inpatient mental health treatment facilities | See inpatient task book |  | TBD |
| Develop a referral network | 1. Establish relationships with outpatient and inpatient providers. 2. Create protocols for making referrals to providers. | Referral protocols, relationships with providers | Approved outpatient and inpatient providers Establishing Relationships Referral Guidance |  | TBD |
| Establish protocols to protect members experiencing behavioral health concerns | 1. Research best practices for protecting members. 2. Develop protocols for protecting members. | Protocols for following up with members, documentation policies, safety protocols | Protecting your members |  | TBD |
| Evaluate existing resources annually | 1. Review current resources and services. 2. Evaluate their effectiveness and identify areas for improvement. | Current available resources and services | Internal agency data and metrics Sample Evaluation Survey |  | Annually |