| Tasks | Components | Resources | Project Manager | Status/Completion Date |
| --- | --- | --- | --- | --- |
| Identify Team Coordinator | - Define Roles and Responsibilities | Team Coordinator Roles and responsibilities examples |  |  |
|  | - Determine application and nomination process | Sample Team Coordinator Application |  |  |
|  | - Coordinate with Administrators/Union on potential applicants |  |  |  |
| Identify Peer Team Members | - Determine the qualities of a Peer Supporter | Peer Team member qualities |  |  |
|  | - Send a survey to the department in an attempt to let them choose. | Sample survey questions |  |  |
|  | - Determine the process for joining the Peer Support Team (application Process) | Sample application form |  |  |
|  | - Determine the requirements of the Peer Support Team Members | Peer team member requirements |  |  |
|  | - Consider assigning Shift Leads to maintain the oversight of each shift and the members assigned to each shift. |  |  |  |
| Develop your Peer Team SOP/SOG, this should be integrated into the BHAP as a whole. This sample is created as a standalone component. See Leadership task book for full SOP | - Purpose | Peer Support SOP components Sample Peer Support SOP |  |  |
|  | - Background |  |  |  |
|  | - Mission Statement |  |  |  |
|  | - Positions and Roles, Responsibilities and Requirements for each |  |  |  |
|  | - Chain of command |  |  |  |
|  | - Activation process and how member may access the team |  |  |  |
|  | - Confidentiality components | Sample confidentiality agreement |  |  |
| Train your Peer Support Team | - Identify the training that will suit the needs of your organization | https://ucfrestores.com/training/peer-support/react-training-program/ https://www.iaff.org/peer-support/ https://www.facebook.com/NSU.FRRT/about https://www.ilffps.org/register/ Front Page - North Carolina First Responder Peer Support (ncffps.org) |  |  |
|  | - Ensure that all team members complete the initial training requirements |  |  |  |
|  | - Specify the Trainings that will be required for your Team Members | (Technician level training specified in “education” section of toolkit,) |  |  |
| Obtain buy in from the members and perform an informational campaign | - Develop a list of talking points to be discussed |  |  |  |
|  | - Conduct routine visits to meet the members in a comfortable setting, these should be done at least once a year. |  |  |  |
|  | - Allow members to ask questions and provide feedback to those questions |  |  |  |
|  | - Take input from the members and allow them to have a say in the team (when appropriate) |  |  |  |
|  | - Send resources to your members for access outside of work. | Samples of outside access to resources |  |  |
| Maintain your program | - Plan meetings with your team (Preferably at least biannually) |  |  |  |
|  | - Maintain your running roster list and conduct regular recruiting campaigns |  |  |  |
|  | - Encourage peers to register on Redline Rescue. | https://redlinerescue.org/ |  |  |
|  | - Maintain the list of vetted clinicians and services |  |  |  |
|  | - Track Peer Team outreaches and prevalent issues within your agency | Peer contact tracking form |  |  |
|  | - Track your peer team’s CEUs and ensure that criteria is being met | Sample CEU tracking form |  |  |
|  | - Network with other peer support teams in your area or region |  |  |  |
| Evaluate your program | - Collect and analyze the results of your evaluation | Sample evaluation process |  |  |
|  | - Make changes according to the results of your program evaluation |  |  |  |